Table of Contents

# Statement of Work: @jax-data-science/image-visualization — Image Visualization Library Extraction

Version: 1.1 Date: May 2026 Author: Jax Image Tools Team Status: Draft — awaiting plan selection

Changes since 1.0:

- Renamed the package from @jax/jit-plotting to @jax-data-science/image-visualization. The new name describes the product (image visualization for data science) rather than the codename of the work (JIT plotting). The internal codename "JIT-PLOTTING" is preserved in this document's filename only.

- DiagramComponent removed from extraction scope. It is the consumer of the library, not part of it. It stays in apps/jit-ui and is rewired to use the library's services through host-supplied port implementations.

- RegionEditorComponent moved to deferred scope. Whether it (or parts of it) belong in the library is a separate assessment, to be made after the service layer ships. Default assumption: it stays in apps/jit-ui.

- Effort estimates updated to reflect the smaller default scope.

- Open questions reorganized — the components decision is now the headline deferred question.

## 1. Background

The jit-ui Angular SPA contains roughly 8,100 lines of code that implement the image plotting and region-editing surface — PlotlyService, the DiagramComponent, the RegionEditorComponent, the wand / vertex-eraser / zoom-to-box tool services, the geometry helpers, and the Region / Shape data models.

The services in that surface (everything except the two top-level components) are the largest cohesive subsystem in jit-ui that is not specific to JIT's back-end APIs. Other Angular front-ends inside The Jackson Laboratory could benefit from the same Plotly-based image viewer with region editing and on-canvas tooling, but the code is currently entangled with jit-ui's MainState, MainFacade, FilesService, and the JIT-specific ZoomRequest contract.

The components (DiagramComponent and RegionEditorComponent) sit one layer above. DiagramComponent is the host's viewer page — it owns jit-ui-specific toolbar layout, keybindings, the pipeline-dialog launch button, and the MainFacade wiring. It is a consumer of the library, not part of it. RegionEditorComponent is more ambiguous — its table and editor might generalize, but it currently leans heavily on MainFacade, MainUtilities, and FilesService.

This SOW evaluates the cost and reach of carving the service layer into a reusable library named @jax-data-science/image-visualization, and presents four candidate plans. Whether any part of RegionEditorComponent follows the services into the library is treated as a deferred decision.

## 2. Scope Inventory

### 2.1 What is being extracted (default scope)

| Area | Files | LOC (incl. specs) | Coupling to host app |
| --- | --- | --- | --- |
| Region / Shape models | main/models/plotting/{region,shape}.ts | 224 | None — pure TS |
| Geometry helpers | services/plotting/geometry.ts | 158 | None |
| Plot utilities | main/plot.utilities.ts | 613 | Uses file-saver; otherwise pure |
| Tool services | wand*.ts, vertex-eraser*.ts, zoom-to-box*.ts | 1,624 | Already use bindHost({...}) pattern |
| PlotlyService | services/plotting/plotly.service.ts | 1,446 | Heavy — MainState, FilesService, MessageService, HttpClient, ZoomRequest, DisplayType |
| Default total |  | ~4,065 |  |

### 2.2 What stays in jit-ui

The following remain in the host app, both because they are JIT-specific and because they sit above the library layer:

- DiagramComponent — definitively stays. It is the library's consumer in jit-ui. After extraction it injects PlotlyService from @jax-data-science/image-visualization and supplies the host-side port implementations through DI.

- RegionEditorComponent — stays by default. Reassessed after the service layer lands (see §11, Q1).

- MainState, MainFacade, MainUtilities (host state container)

- FilesService (the JIT API client)

- ZoomRequest (the JIT wire contract)

- DisplayType (jit-ui's display-mode routing)

- app-routing.module.ts and toolbar keybindings owned by DiagramComponent

- Auth0 / HttpClient interceptor wiring

### 2.3 Deferred scope (assessed after the service layer ships)

| Area | LOC | Reason for deferral |
| --- | --- | --- |
| RegionEditorComponent | 1,105 | Three jit-ui-specific dependencies (MainFacade, MainUtilities, FilesService) need to be untangled before the component can move. The library is useful without it. |

If post-extraction analysis shows that the editor's table, GeoJSON I/O, and shape-list management would benefit other consumers, a follow-up phase can carve a subset into the library — for example, a stateless RegionTable component that takes shapes as @Input() and emits edits as @Output(). That subset is not estimated here.

### 2.4 Port surface

Whatever the library boundary, the same five host-supplied ports are required. These are sketched in libs/jit-plotting/src/ports/:

- ImageStatePort — read/write the host's image state (filename$, isImageCached$, loading flags, etc.)

- ZoomBackendPort — server-side zoom round-trip (replaces direct FilesService.zoomOnRegion)

- FileLoaderPort — auth'd image fetch (replaces direct HttpClient)

- NotificationPort — toast/snackbar abstraction (replaces direct MessageService)

- NavigationPort — display-type/tab routing hook (replaces direct FilesService.selectDisplayType)

DiagramComponent provides all five port implementations to the library through its module-level DI providers.

## 3. Goals

| # | Goal | Measurable end state |
| --- | --- | --- |
| G1 | Decouple plotting from JIT-specific state | PlotlyService no longer imports MainState, FilesService, MessageService, or ZoomRequest |
| G2 | Make the library independently testable | The library's spec suite runs without apps/jit-ui being present in the workspace |
| G3 | Preserve every existing user-facing feature | Every flow exercised through DiagramComponent today behaves identically after extraction: region draw/edit/export, wand selection, vertex eraser, zoom-to-box, stack viewing, surface plot, GeoJSON I/O, and the pipeline-dialog smoke test |
| G4 | No regression in build time or bundle size | Production bundle size within ±2% of pre-extraction baseline |
| G5 | Make the library reusable | Depending on plan, either consumable by other Nx apps in this workspace (Plans A/B/D) or by external Angular apps via npm (Plan B), or by non-Angular apps (Plan C) |

## 4. Non-Goals

- Rewriting any of the plotting logic. This is a relocation + decoupling exercise, not a refactor of how shapes are stored, how Plotly is configured, or how the wand samples pixels.

- Moving DiagramComponent. It is the host's viewer page and stays in apps/jit-ui. Updating it to consume the library is in scope; relocating it is not.

- Moving RegionEditorComponent in the default plan. A follow-up assessment can revisit whether a stateless subset of it belongs in the library.

- Adding new features. No new tools, no new region types, no new export formats.

- Replacing Plotly. The library is and remains a Plotly.js wrapper.

- Publishing to public npm. Internal registry only.

## 5. Candidate Plans

Four plans are presented in increasing order of ambition, cost, and reach.

Reach →
            ┌────────────────────────────────────────────────────────────────────┐
            │  D     A          B                              C                  │
   Effort   │  •    •          •                              •                   │
     ↑      │  1d   5d         6d                            ~14d                 │
            │ pure services   services                      services               │
            │ only  Nx only   Nx + npm                  npm + non-Angular          │
            └────────────────────────────────────────────────────────────────────┘

### Plan A — Workspace library, never published

Summary: Create libs/image-visualization as a buildable Nx library. Move the service layer in (pure models, geometry, plot utilities, tool services, PlotlyService). DiagramComponent stays in apps/jit-ui and is rewired to consume the library via DI. Consumed from apps/jit-ui via a workspace path mapping. Not published.

What you get:

- Clean separation of concerns inside this monorepo

- Independent test suite, independent TS project, independent lint config

- Foundation that Plan B can extend later if a second consumer appears

What you don't get:

- Cross-repository reuse — other Jackson Lab Angular apps cannot consume it without copying the source

Effort: 5 working days

- Phase 0: scaffold lib (0.5d)

- Phase 1: move pure layer — region, shape, geometry, plot-utilities (0.5d)

- Phase 2: move tool services — wand, vertex-eraser, zoom-to-box (1d)

- Phase 3: port surgery on PlotlyService + move (3d) ← highest risk

There is no Phase 4 in this plan — DiagramComponent is updated in place, not moved. The update (swap direct service injections for library injections, register host port adapters in app.module.ts) is part of Phase 3's acceptance criteria, not a separate phase.

Risk: Moderate. All risk concentrated in Phase 3. Mitigation: keep plotly.service.spec.ts green at every step; add an end-to-end smoke test before starting.

When to pick this:

- jit-ui will likely remain the sole consumer for ≥12 months

- Want the separation-of-concerns benefit without committing to a publishing pipeline

- Have a small team (1 dev) and want the lowest-risk path that still delivers a real library

### Plan B — Publishable Angular library (recommended)

Summary: Plan A plus ng-packagr build, npm metadata, and a publishing target. Library is published to the internal registry (GitHub Packages or JAX-hosted Verdaccio) at @jax-data-science/image-visualization. apps/jit-ui continues to consume from the workspace; external consumers consume from npm.

What you get:

- Everything Plan A delivers

- A versioned artifact other Angular apps can npm install

- Semver-disciplined release cycle, changelog, deprecation policy

Effort: 6 working days

- Plan A (5d)

- Phase 5: publish pipeline (1d) — ng-package.json, CI release job, registry auth, README badges, semver tagging

Risk: Same as Plan A. Publishing adds operational overhead, not engineering risk.

Operational ongoing cost: ~½ day per release. Realistic cadence: 1–2 releases per quarter.

When to pick this:

- At least one other Angular consumer is likely within 6 months

- Have buy-in for the release process (someone owns npm publish)

- The library will be the canonical image visualization implementation across JAX

### Plan C — Framework-agnostic core + Angular adapter

Summary: Split into two packages:

- @jax-data-science/image-visualization-core — pure TypeScript. No Angular. Owns the Plotly wrapper, tool engines, geometry, region/shape models, plot utilities. Framework-agnostic. Consumable from React, Vue, vanilla JS, Node test harnesses, etc.

- @jax-data-science/image-visualization-angular — Angular library that wraps the core in injectable services and supplies the port DI tokens.

What you get:

- Maximum reach: any front-end framework can consume the core

- A clean test boundary — the core can be tested with plain Jest, no Angular TestBed

- Future-proof against jit-ui ever migrating off Angular

What it costs:

- Significantly more refactoring. PlotlyService today freely uses Injectable, BehaviorSubject, Observable, Subject, RxJS subscriptions, and Angular DI. All of these have to either move to the Angular adapter or be re-expressed with framework-agnostic primitives (callbacks, plain event emitters, AbortControllers, or a small RxJS-only core — RxJS is acceptable without Angular).

- The Plan C split is in the services. UI components are out of scope here too — DiagramComponent and RegionEditorComponent stay in jit-ui (Angular-bound).

Effort: ~14 working days

- Plan B (6d)

- Phase 6: split the core (5d) — extract Plotly wrapper, move RxJS usage behind framework-neutral interfaces, rewrite tests against Jest-only

- Phase 7: write Angular adapter (2d) — re-add @Injectable decorators in the adapter package, re-wire DI

- Phase 8: validation (1d) — prove the core works in a non-Angular harness (smallest credible test: render a Plotly heatmap from a plain HTML page)

Risk: Significant. The split increases surface area, doubles the maintenance overhead, and introduces a layer of indirection. Only worth doing if a non-Angular consumer is genuinely on the roadmap.

When to pick this:

- A specific non-Angular consumer is committed (e.g., a planned React rewrite of a sibling tool)

- The team has bandwidth for ~3 weeks of focused work

- Long-term, JAX wants this library to be the standard imaging viewer across all frontend stacks

### Plan D — Minimal carve-out (data models only)

Summary: Move only the pure layer — region.ts, shape.ts, geometry.ts, plot.utilities.ts — into libs/image-visualization. Leave PlotlyService, the tool services, and both components in apps/jit-ui.

What you get:

- Shareable data models for any project that needs to read/write JIT region GeoJSON

- ~1,000 LOC of pure TS in a clean package

- A foothold for future expansion

What you don't get:

- Any of the actual plotting / UI surface — consumers still have to bring their own Plotly wrapper

- Real separation inside jit-ui — PlotlyService still imports MainState, etc.

Effort: 1 working day

Risk: Negligible. The pure files have no DI, no host coupling, no framework dependency.

When to pick this:

- The primary motivation is sharing region/shape interchange with a back-end tool, notebook, or sibling repo — not UI reuse

- Want a low-cost first step that proves out the Nx library workflow before committing to Plan A/B

- Useful as a pre-Plan-A migration step — Plan A naturally absorbs Plan D's work

## 6. Plan Comparison

|  | A — workspace lib | B — publishable lib | C — core + adapter | D — models only |
| --- | --- | --- | --- | --- |
| Effort | 5 days | 6 days | ~14 days | 1 day |
| Risk | Moderate | Moderate | High | Negligible |
| DiagramComponent | Stays in jit-ui | Stays in jit-ui | Stays in jit-ui | Stays in jit-ui |
| RegionEditorComponent | Deferred decision | Deferred decision | Deferred decision | Stays in jit-ui |
| Cross-repo reuse (Angular) | No | Yes | Yes | Partial (models) |
| Cross-framework reuse | No | No | Yes | Partial (models) |
| Ongoing release cost | None | ~½ day / release | ~1 day / release | None |
| Reversible | Yes | Yes | Partially (split is sticky) | Yes |
| Recommended for jit-ui today | If sole consumer | Yes | Only with a committed non-Angular consumer | As a stepping stone |

## 7. Recommendation

Plan B, with the following rationale:

- The cost delta over Plan A is one day. Once you've done Plan A, adding ng-packagr + a CI release job is mechanical. There is no good engineering reason to stop at Plan A unless you are absolutely certain there will never be a second consumer.

- Plan C is overbuilt for the current need. No concrete non-Angular consumer exists. Doing Plan C speculatively burns ~2 weeks for reach that may never be used. Plan B does not foreclose Plan C — the core/adapter split can be introduced later if a real React consumer materializes.

- Plan D leaves the meat of the problem unaddressed. The reason this extraction was raised is that PlotlyService is a 1,400-line god-object tangled with jit-ui state. Plan D moves the easy 1,000 lines and leaves the hard 1,400 in place.

The 6-day estimate assumes one developer with familiarity with the codebase working uninterrupted. Add ~30% if the work is shared across multiple contributors or interleaved with feature work.

A follow-up assessment of RegionEditorComponent is recommended once the service layer lands — see §11 Q1.

## 8. Phased Delivery Schedule (Plan B)

| Phase | Deliverable | Effort | Risk |
| --- | --- | --- | --- |
| 0 | Library scaffold (nx g library image-visualization, path mapping, empty exports) | 0.5d | Low |
| 1 | Pure layer moved (region, shape, geometry, plot-utilities) | 0.5d | Low |
| 2 | Tool services moved (wand, vertex-eraser, zoom-to-box) | 1d | Low |
| 3 | PlotlyService port surgery + move; DiagramComponent rewired in place | 3d | High |
| 5 | Publish pipeline (ng-package.json, release CI, semver, README) | 1d | Low |

There is no Phase 4 in the current plan — DiagramComponent is updated in Phase 3 (swapping direct service injections for library injections and registering port adapters), not moved. The Phase numbering preserves "5" for publishing so that the optional component-extraction work (formerly Phase 4) can slot back in cleanly if the deferred decision lands on "move parts of RegionEditorComponent".

End conditions:

- npm run build passes for apps/jit-ui and libs/image-visualization

- npm test passes — including the existing plotly.service.spec.ts, wand.service.spec.ts, region.spec.ts, shape.spec.ts, geometry.spec.ts, plot.utilities.spec.ts, zoom-to-box-tool.service.spec.ts. The diagram.component.spec.ts and region-editor.component.spec.ts stay in apps/jit-ui and continue to pass.

- Manual smoke test: open an image, draw a freeform region, switch to another image, switch back (regions persist), zoom in (server round-trip), wand select, vertex erase, export to GeoJSON, re-import GeoJSON

- Production bundle size within ±2% of baseline

- Library publishes to the internal registry at @jax-data-science/image-visualization@0.1.0

## 9. Risks & Mitigations

| # | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Phase 3 introduces a regression in the zoom round-trip (the most complex method in PlotlyService) | Moderate | High | Migrate one call site at a time; keep specs green between each; manual smoke test the zoom path daily |
| R2 | MainState adapter ends up leaking host concerns through the port (e.g., the port grows methods that exist only to satisfy MainState's shape) | Moderate | Moderate | Design the port from the library's perspective, not by mirroring MainState. Reject any port method that doesn't have a non-jit-ui justification |
| R3 | DiagramComponent's wiring to the library is more invasive than expected — its template binds directly to fields the service used to expose | Moderate | Moderate | Keep the service's public surface stable. If a binding must change, add a thin getter to the component rather than restructuring the library API |
| R4 | PrimeNG version skew between the library and consuming apps | Low | Moderate | Treat primeng as a peerDependency, not a dependency. Document supported PrimeNG version range in the library README |
| R5 | Specs that today rely on jit-ui's TestBed configuration break when moved | Moderate | Low | Move specs alongside their source files; rewrite TestBed setup to use only library imports + mock ports |
| R6 | The release pipeline (Phase 5) stalls on registry auth or CI permissions | Moderate | Low | Spike the publish flow before Phase 0; confirm registry credentials and GitHub Actions permissions on day 1 |

## 10. Dependencies & Prerequisites

- Nx @nx/angular:library generator is already available (Nx 16.10.0)

- libs/ directory exists and is empty (no migration cleanup needed)

- The bindHost({...}) pattern is already established in tool services — no new architectural primitive required

- Internal npm registry exists and accepts @jax-data-science/* scoped packages (verify before Phase 5)

## 11. Open Questions

- Should any part of RegionEditorComponent move into the library? To be assessed after the service layer ships. Three plausible outcomes:

  - Stay in jit-ui as-is. Cleanest. Editor remains a jit-ui-specific consumer of the library's Region / Shape models. Likely default.

  - Carve out a stateless table. Extract a RegionTable component that takes shapes as @Input() and emits edits as @Output(). ~1–2 days of work. Useful if the editor table itself is reusable.

  - Move the whole editor. Requires untangling MainFacade, MainUtilities, and FilesService from the editor first. ~2–3 days. Probably overkill.

- Recommend revisiting this question after Phase 3 lands and the port surface has been validated against real usage.

- Registry target. Internal Verdaccio, GitHub Packages, or JFrog? Affects Phase 5 design.

- Version starting point. 0.1.0 (signaling pre-stable API) or 1.0.0 (signaling this is the canonical implementation)? Recommendation: 0.1.0.

- Second consumer. Is there a second Angular front-end at JAX that would adopt @jax-data-science/image-visualization within 6 months? If unambiguously no, Plan A becomes more defensible.

- Directory name on disk. The sketch lives at libs/jit-plotting/ (the work codename). At Phase 0, scaffold the real library at libs/image-visualization/ to match the package name. Move the sketch contents over and delete the codename directory.

## Appendix A — Files Referenced

Sketch implementation (work codename "jit-plotting" — directory renames to libs/image-visualization/ at Phase 0):

- libs/jit-plotting/README.md — package overview

- libs/jit-plotting/EXTRACTION_PLAN.md — original phased plan (predates the rename and the components-stay-in-jit-ui decision; superseded by §8 of this SOW)

- libs/jit-plotting/src/ports/ — port interfaces

- libs/jit-plotting/src/tokens.ts — Angular DI tokens

- libs/jit-plotting/src/plotly.service.shim.ts — before/after constructor sketch

Source under extraction (moves into the library):

- apps/jit-ui/src/app/services/plotting/ — plotly.service.ts and tool services

- apps/jit-ui/src/app/main/models/plotting/ — region.ts, shape.ts

- apps/jit-ui/src/app/main/plot.utilities.ts — utilities and constants

Source that stays in jit-ui (rewired to consume the library):

- apps/jit-ui/src/app/main/components/diagram/ — DiagramComponent (host viewer page, consumer of the library)

- apps/jit-ui/src/app/main/components/region-editor/ — RegionEditorComponent (deferred decision; see §11 Q1)